## Sheet1
newid | Staff/Position | MFO | Major Category | Task/Terms of Reference (ToR) | E: Measure of Effectiveness (Numeric Output) | Q: Measure of Quality | T: Measure of Time (Updated per request) | Areas | Charging Code
1 | A.C. Flores | MFO 2. Technologies | Advanced Analytics (Ensemble modelling) | 1. Lead in reporting monthly accomplishments under this function/project | Monthly summary report of accomplishments produced | Monthly reports submitted to unit head, and presented during monthly meetings | January to June 2026 | Within the Philippines | TCC-300-001
2 | A.C. Flores | MFO 2. Technologies | Advanced Analytics (Ensemble modelling) | 2. Lead in coordination with Data Lake on identification of possible data sources | One (1) inventory of data used in ensemble modelling produced. | Complete and accessible through Data Lake APIs | January to June 2026 | Within the Philippines | TCC-300-001
3 | A.C. Flores | MFO 2. Technologies | Advanced Analytics (Ensemble modelling) | 3. Lead data preprocessing for ensemble base models | One (1) dataset to be used for ensemble modelling. | Cleaned and pre-process dataset. | January to June 2026 | Within the Philippines | TCC-300-001
4 | A.C. Flores | MFO 2. Technologies | Advanced Analytics (Ensemble modelling) | 4. Lead in base model selection, training and evaluation | One (1) base model used for ensemble modelling | With generated model diagnostics, performance metrics and model predictions. | January to June 2026 | Within the Philippines | TCC-300-001
5 | A.C. Flores | MFO 2. Technologies | Advanced Analytics (Ensemble modelling) | 5. Lead in ensemble model construction, training and evaluation | One (1) ensemble model for production, area and yield (PAY) | With generated ensemble model diagnostics, performance metrics and model predictions. | January to June 2026 | Within the Philippines | TCC-300-001
6 | A.C. Flores | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Sandbox | 6. Lead in one (1) regular ideation session | One (1) brief writeup of the featured topic/idea produced. | Brief writeup of the featured topic/idea. | January to June 2026 | Within the Philippines | TCC-300-001
7 | A.C. Flores | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Support Services (Consultation) | 7. Manage consultation requests, consultation schedule, consultant assignments and monitor feedback from clients | Consultation services provided to 100% of clients assigned to staff. | Concern of client properly addressed and documented through the consultant's report and client feedback survey. | January to June 2026 | Within the Philippines | TCC-300-001
8 | A.C. Flores | MFO 3. Extension support, educations and traiing services (ESSETS) | DAC Training services | 8. Assist in the conduct of training services to PhilRice staff | At least one (1) training conducted. | With documented proof of attendance and participation as instructor and training materials compiled | By June 2026 | Within the Philippines | TCC-300-001
9 | A.C. Flores | MFO 4. R&D Services | Core Analytics (Production, Area and Yield) | 9. Lead in development, maintenance of command center dashboards and shiny web apps related to Production, Area and Yield | One (1) dashboard/shiny web application developed and maintained. | Fully functional. Maintained and improved as necessary. | By June 2026 | Within the Philippines | TCC-300-001
10 | A.C. Flores | MFO 4. R&D Services | Core Analytics (Production, Area and Yield) | 10. Lead the presentation and demonstration of command center dashboards and Shiny web applications focused on Production, Area and Yield insights to intended clients | One presentation/demonstrations of shiny web app/dashboard conducted for intended cleints. | With proper documentation of presentation, and dashboard accessible through the RiceLytics Executive portal. | January to June 2026 | Within the Philippines | TCC-300-001
11 | A.C. Flores | MFO 4. R&D Services | Rapid response Analytics (Operational Analytics) | 11. Respond to data analytics requests classified for rapid-response analytics related to Production, Area and Yield | Provided data analytics services to 100% of the rapid response analytics requests related to Production, Area and Yield. | With documentation report for each rapid response | January to June 2026 | Within the Philippines | TCC-300-001
12 | A.C. Flores | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 12. Represent the Analytics unit in meetings where attendance of DAC-Analytics unit is needed, in the absence of the unit head | Meeting/s attended in the absence of the unit head. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
13 | A.C. Flores | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 13. Report the status of activities and accomplishments of Analytics unit when needed, in the absence of the unit head | 1 unit summary report of accomplishments, when needed. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
14 | A.C. Flores | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 14. Ensure all analytics unit processes are documented, data used are retrieved solely from the DAC-Data Lake and newly generated data and data products are properly stored in the DAC data lake | 100% of analytics unit data and process documentation stored in the DAC-Data Lake. | Complete, secured and accessible | January to June 2026 | Within the Philippines | TCC-300-001
15 | A.C. Flores | MFO 7. Improved Governance | Data Liaison | 15. Lead in data liaising, coordinating with Data Lake unit on monitoring of all available data to be used for all analytics projects and tasks within the unit | Provided data availability and data sources report to 100% of analytics projects and tasks. | List of data available for use, accessible through Data Lake APIs | January to June 2026 | Within the Philippines | TCC-300-001
16 | A.C. Flores | MFO 7. Improved Governance | Upscaling and development of Data Analytics Capabilities | 16. Assist and participate in coordination of activities and trainings under this collaborative project | One (1) activity/training/task accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
17 | A.C. Flores | MFO 7. Improved Governance | Institution and Center Related Activities | 17. Assist in other project activities as instructed by the supervisor | Tasks assigned by the supervisor are accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
18 | A.C. Flores | MFO 7. Improved Governance | Institution and Center Related Activities | 18. Attend workshops or trainings as per invitation | Attended workshop or training as per invitation. | With documented proof of attendance, participation or completeion. | As per invitation, within January to June 2026 | Within the Philippines | TCC-300-001
19 | A.C. Flores | MFO 7. Improved Governance | Institution and Center Related Activities | 19. Participate in institutional activities | Participated in institutional activities. | As documented in attendance sheets | January to June 2026 | Within the Philippines | TCC-300-001
20 | A.C. Flores | MFO 7. Improved Governance | Institution and Center Related Activities | 20. Comply with Integrated Management System (IMS) Policy, Procedures, Programs, and Projects of PhilRice | Integrated Management System (IMS) Policy, Procedures, Programs and Projects of PhilRice are complied. | based on ISO guideline | January to June 2026 | Within the Philippines | TCC-300-001
21 | E.M.S. Gatchalian | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 1. Assist in exploration of new methodologies and model frameworks best suited for rice trajectory models | One (1) model framework for rice trajectory models produced. | complete with proper documentation | January to June 2026 | Within the Philippines | TCC-300-001
22 | E.M.S. Gatchalian | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 2. Assist in data cleaning and preprocessing of local data needed for the rice trajectory model | One (1) dataset needed for modeling rice trajectories | Cleaned and pre-processed | January to June 2026 | Within the Philippines | TCC-300-001
23 | E.M.S. Gatchalian | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 3. Assist in rice trajectory model deployment and monitoring and web app development | One (1) web application showing projections produced. One (1) set of projections generated from trajectory models | Projections and web application are complete and accessible through the RiceLytics Executive website | January to June 2026 | Within the Philippines | TCC-300-001
24 | E.M.S. Gatchalian | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Sandbox | 4. Lead in at least one (1) regular ideation session | One (1) brief writeup of the featured topic/idea of the ideation session produced. | Brief writeup of the featured topic/idea. | January to June 2026 | Within the Philippines | TCC-300-001
25 | E.M.S. Gatchalian | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Support Services (Consultation) | 5. Serve as consultant catering to consultation requests | Consultation services provided to 100% of clients assigned to staff. | Concern of client properly addressed and documented through the consultant's report and client feedback survey. | January to June 2026 | Within the Philippines | TCC-300-001
26 | E.M.S. Gatchalian | MFO 3. Extension support, educations and traiing services (ESSETS) | DAC Training services | 6. Assist in the conduct of training services to PhilRice staff | At least one (1) training conducted. | With documented proof of attendance and participation as instructor and training materials compiled | By June 2026 | Within the Philippines | TCC-300-001
27 | E.M.S. Gatchalian | MFO 3. Extension support, educations and traiing services (ESSETS) | Upscaling and development of Data Analytics Capabilities | 7. Assist and participate in coordination of activities and trainings under this collaborative project | One (1) activity/training/task accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
28 | E.M.S. Gatchalian | MFO 4. R&D Services | Core Analytics (PhilRice Projects and other rice related data) | 8. Co Lead in development, maintenance of command center dashboards and shiny web apps related to PhilRice R&D Projects and other rice related data | One (1) dashboard/shiny web application developed and maintained. | Fully functional. Maintained and improved as necessary. | By June 2026 | Within the Philippines | TCC-300-001
29 | E.M.S. Gatchalian | MFO 4. R&D Services | Core Analytics (PhilRice Projects and other rice related data) | 9. Lead the presentation and demonstration of command center dashboards and Shiny web applications focused on PhilRice R&D Projects and other rice related data intended clients | One presentation/demonstrations of shiny web app/dashboard conducted for intended cleints. | With proper documentation of presentation, and dashboard accessible through the RiceLytics Executive portal. | By June 2026 | Within the Philippines | TCC-300-001
30 | E.M.S. Gatchalian | MFO 4. R&D Services | Rapid response Analytics (Operational Analytics) | 10. Lead data analysis of requests classified for rapid-response analytics focused on focused on rice farmers and their characteristics | Provided data analytics services to 100% of the rapid response analytics requests. | Provided data analytics services. | By June 2026 | Within the Philippines | TCC-300-001
31 | E.M.S. Gatchalian | MFO 7. Improved Governance | Data Analytics on relevant rice industry news and current affairs (C) | 11. Lead in monitoring for data analytics potential and opportunities on news, policies and current affairs relating to rice industry | Provided relevant updates on rice data related news, policies and current affairs. | Updated weekly with proper documentation and accessible to other analytics unit members | January to June 2026 | Within the Philippines | TCC-300-001
32 | E.M.S. Gatchalian | MFO 7. Improved Governance | Institution and Center Related Activities | 12. Assist in other project activities as instructed by the supervisor | Tasks assigned by the supervisor are accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
33 | E.M.S. Gatchalian | MFO 7. Improved Governance | Institution and Center Related Activities | 13. Attend workshops or trainings as per invitation | Attended workshop or training as per invitation. | With documented proof of attendance, participation or completeion. | As per invitation, within January to June 2026 | Within the Philippines | TCC-300-001
34 | E.M.S. Gatchalian | MFO 7. Improved Governance | Institution and Center Related Activities | 14. Participate in institutional activities | Participated in institutional activities. | As documented in attendance sheets | January to June 2026 | Within the Philippines | TCC-300-001
35 | E.M.S. Gatchalian | MFO 7. Improved Governance | Institution and Center Related Activities | 15. Comply with Integrated Management System (IMS) Policy, Procedures, Programs, and Projects of PhilRice | Integrated Management System (IMS) Policy, Procedures, Programs and Projects of PhilRice are complied. | based on ISO guideline | January to June 2026 | Within the Philippines | TCC-300-001
36 | H.G. Vigilia | MFO 2. Technologies | Advanced Analytics (Geoinformatics and spatial analytics) | 1. Lead in reporting monthly accomplishments under this function/project | Monthly summary report of accomplishments produced | Monthly reports submitted to unit head, and presented during monthly meetings | January to June 2026 | Within the Philippines | TCC-300-001
37 | H.G. Vigilia | MFO 2. Technologies | Advanced Analytics (Geoinformatics and spatial analytics) | 2. Lead in coordination with Data Lake and SPINLAB team on identification of possible data sources of spatial data, satellite data, remote- sensing data to be used for spatial hyperlocal rice profiling | Identify and document one (1) new data sources for spatial analysis. | Included in Data Catalog, with metadata | January to June 2026 | Within the Philippines | TCC-300-001
38 | H.G. Vigilia | MFO 2. Technologies | Advanced Analytics (Geoinformatics and spatial analytics) | 3. Lead in generation granular and hyperlocal profiling of rice industry through spatial modelling and GIS visualizations | One (1) dataset/ feature/ variable preprocessed. One (1) consolidated spatial dataset. One (1) GIS visualization/ map generated. | Complete, accurate, and forwarded to Data Lake Unit, with proper documentation | January to June 2026 | Within the Philippines | TCC-300-001
39 | H.G. Vigilia | MFO 2. Technologies | Advanced Analytics (Geoinformatics and spatial analytics) | 4. Lead in exploration of new methodologies and spatio temporal model frameworks focusing on spatio-temporal variables affecting rice production, area and yield | Reviewed one (1) new methodology or model framework | Used in constructing new spatio-temporal model of rice production. | January to June 2026 | Within the Philippines | TCC-300-001
40 | H.G. Vigilia | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Sandbox | 5. Document the proceedings and outputs of regular ideation sessions | Written documentation of sandbox session outputs/discussions produced. | Session materials and outputs are complete and accessible by DAC staff | January to June 2026 | Within the Philippines | TCC-300-001
41 | H.G. Vigilia | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Sandbox | 6. Lead the coordination and scheduling of sandbox session(s), as needed and depending on availability | Successfully coordinated and scheduled at least one (1) sandbox session. | Session successfully conducted, with proper documentation | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
42 | H.G. Vigilia | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Support Services (Consultation) | 7. Serve as consultant catering to consultation requests | Consultation services provided to 100% of clients assigned to staff. | Concern of client properly addressed and documented through the consultant's report and client feedback survey. | January to June 2026 | Within the Philippines | TCC-300-001
43 | H.G. Vigilia | MFO 4. R&D Services | Core Analytics (Climate and Environment) | 8. Lead in development, maintenance of command center dashboards and shiny web apps related to Climate and Environment factors affecting Rice productivity | One (1) dashboard/shiny web application developed and maintained. | Fully functional. Maintained and improved as necessary. | By June 2026 | Within the Philippines | TCC-300-001
44 | H.G. Vigilia | MFO 4. R&D Services | Core Analytics (Climate and Environment) | 9. Lead the presentation and demonstration of command center dashboards and Shiny web applications focused on Climate and Environment factors affecting Rice productivity to the intended clients | One presentation/demonstrations of shiny web app/dashboard conducted for intended cleints. | With proper documentation of presentation, and dashboard accessible through the RiceLytics Executive portal. | January to June 2026 | Within the Philippines | TCC-300-001
45 | H.G. Vigilia | MFO 4. R&D Services | Rapid response Analytics (Operational Analytics) | 10. Lead data analysis of requests classified for rapid-response analytics focused on Climate and Environment factors affecting Rice productivity | Provided data analytics services to 100% of the rapid response analytics requests related to technologies, program interventions, and policies impacting rice productivity | With documentation report for each rapid resonse | January to June 2026 | Within the Philippines | TCC-300-001
46 | H.G. Vigilia | MFO 7. Improved Governance | Upscaling and development of Data Analytics Capabilities | 11. Assist and participate in coordination of activities and trainings under this collaborative project | One (1) activity/training/task accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
47 | H.G. Vigilia | MFO 7. Improved Governance | Institution and Center Related Activities | 12. Assist in other project activities as instructed by the supervisor | Tasks assigned by the supervisor are accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
48 | H.G. Vigilia | MFO 7. Improved Governance | Institution and Center Related Activities | 13. Attend workshops or trainings as per invitation | Attended workshop or training as per invitation. | With documented proof of attendance, participation or completeion. | As per invitation, within January to June 2026 | Within the Philippines | TCC-300-001
49 | H.G. Vigilia | MFO 7. Improved Governance | Institution and Center Related Activities | 14. Participate in institutional activities | Participated in institutional activities. | As documented in attendance sheets | January to June 2026 | Within the Philippines | TCC-300-001
50 | H.G. Vigilia | MFO 7. Improved Governance | Institution and Center Related Activities | 15. Comply with Integrated Management System (IMS) Policy, Procedures, Programs, and Projects of PhilRice | Integrated Management System (IMS) Policy, Procedures, Programs and Projects of PhilRice are complied. | based on ISO guideline | January to June 2026 | Within the Philippines | TCC-300-001
51 | J.B. Santos | MFO 2. Technologies | Advanced Analytics (EDA/Modelling of growth drivers) | 1. Lead in reporting monthly accomplishments under this function/project | Monthly summary report of accomplishments produced | Monthly reports submitted to unit head, and presented during monthly meetings | January to June 2026 | Within the Philippines | TCC-300-001
52 | J.B. Santos | MFO 2. Technologies | Advanced Analytics (EDA/Modelling of growth drivers) | 2. Lead in data exploration and feature engineering | Descriptive summaries, pattern recognition, correlation analysis, clustering and/or dimension reductions of three (3) features/variables | Complete, accurate and with proper documentation | January to June 2026 | Within the Philippines | TCC-300-001
53 | J.B. Santos | MFO 2. Technologies | Advanced Analytics (EDA/Modelling of growth drivers) | 3. Lead in data preprocessing for exploratory data analysis (EDA) of sources of rice production growth and/or provincial competitiveness | Cleaned and pre-process one (1) dataset needed for EDA and sources of rice production and/or provincial competitiveness | Complete, accurate and with proper documentation | January to June 2026 | Within the Philippines | TCC-300-001
54 | J.B. Santos | MFO 2. Technologies | Advanced Analytics (EDA/Modelling of growth drivers) | 4. Lead RBFHS yield and cost model improvement activities | One (1) improved yield and (1) base cost model generated. | With generated model diagnostics, performance metrics and model predictions. | January to June 2026 | Within the Philippines | TCC-300-001
55 | J.B. Santos | MFO 2. Technologies | Advanced Analytics (EDA/Modelling of growth drivers) | 5. Lead in exploration of new methodologies and model frameworks to further describe sources of rice production growth and provincial competitiveness | Utilized one (1) new methodology or model framework. | Used in improving existing models and/or generating new models. | January to June 2026 | Within the Philippines | TCC-300-001
56 | J.B. Santos | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Sandbox | 6. Lead in one (1) regular ideation session | One (1) regular ideation session conduction. | Regular ideation session. | January to June 2026 | Within the Philippines | TCC-300-001
57 | J.B. Santos | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Support Services (Consultation) | 7. Manage consultation requests, consultation schedule, consultant assignments and monitor feedback from clients | Consultation services provided to 100% of clients assigned to staff. | Concern of client properly addressed and documented through the consultant's report and client feedback survey. | January to June 2026 | Within the Philippines | TCC-300-001
58 | J.B. Santos | MFO 4. R&D Services | Core Analytics (Impact of programs/Adoption of technologies) | 8. Lead in development, maintenance of command center dashboards, and Shiny web apps related to technologies, program interventions, and policies impacting rice productivity | One (1) dashboard/shiny web application developed and maintained. | Fully functional. Maintained and improved as necessary. | By June 2026 | Within the Philippines | TCC-300-001
59 | J.B. Santos | MFO 4. R&D Services | Core Analytics (Impact of programs/Adoption of technologies) | 9. Lead the presentation and demonstration of command center dashboards and Shiny web applications focused on technologies, program interventions, and policies impacting rice productivity to the intended clients | One presentation/demonstrations of shiny web app/dashboard conducted for intended cleints. | With proper documentation of presentation, and dashboard accessible through the RiceLytics Executive portal. | January to June 2026 | Within the Philippines | TCC-300-001
60 | J.B. Santos | MFO 4. R&D Services | Rapid response Analytics (Operational Analytics) | 10. Lead data analysis of requests classified for rapid-response analytics focused on technologies, program interventions, and policies impacting rice productivity | Provided data analytics services to 100% of the rapid response analytics requests related to technologies, program interventions, and policies impacting rice productivity | With documentation report for each rapid resonse | January to June 2026 | Within the Philippines | TCC-300-001
61 | J.B. Santos | MFO 4. R&D Services | External Project (M&E of RCEF Seed Program) | 11. Assist in the development of the sampling design, size, and procedure of the involved M&E projects | Sampling design, size, and procedure identified and computed for every M&E project. | Complete, accurate, with proper documentation and approved by end-user | By June 2026 | Within the Philippines | TCC-300-001
62 | J.B. Santos | MFO 4. R&D Services | External Project (The Evolving Philippine Rice Economy) | 12. Assist in the conduct of farm-level household survey in assigned sites | Farm-level household survey in all assigned sites conducted. | Survey returns completed, with proper documentation | By June 2026 | Within the Philippines | TCC-300-001
63 | J.B. Santos | MFO 4. R&D Services | External Project (The Evolving Philippine Rice Economy) | 13. Assist in data cleaning, verification, and editing in assigned sites | Datasets in all assigned sites edited, verified, and validated. | Complete, accurate, and with proper documentation | By June 2026 | Within the Philippines | TCC-300-001
64 | J.B. Santos | MFO 4. R&D Services | External Project (The Evolving Philippine Rice Economy) | 14. Assist in the data processing and generation of results | Data processed and output tables produced. | Output tables are complete, accurate, and approved by project team | By June 2026 | Within the Philippines | TCC-300-001
65 | J.B. Santos | MFO 7. Improved Governance | Upscaling and development of Data Analytics Capabilities | 15. Assist and participate in coordination of activities and trainings under this collaborative project | One (1) activity/training/task accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
66 | J.B. Santos | MFO 7. Improved Governance | Institution and Center Related Activities | 16. Assist in other project activities as instructed by the supervisor | Tasks assigned by the supervisor are accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
67 | J.B. Santos | MFO 7. Improved Governance | Institution and Center Related Activities | 17. Attend workshops or trainings as per invitation | Attended workshop or training as per invitation. | With documented proof of attendance, participation or completeion. | As per invitation, within January to June 2026 | Within the Philippines | TCC-300-001
68 | J.B. Santos | MFO 7. Improved Governance | Institution and Center Related Activities | 18. Participate in institutional activities | Participated in institutional activities. | As documented in attendance sheets | January to June 2026 | Within the Philippines | TCC-300-001
69 | J.B. Santos | MFO 7. Improved Governance | Institution and Center Related Activities | 19. Comply with Integrated Management System (IMS) Policy, Procedures, Programs, and Projects of PhilRice | Integrated Management System (IMS) Policy, Procedures, Programs and Projects of PhilRice are complied. | based on ISO guideline | January to June 2026 | Within the Philippines | TCC-300-001
70 | J.E. Malangis | MFO 4. R&D Services | GIS Technical Staff | 1. Lead the generation of maps for the DAC dashboard to provide data visualizations of tabular rice and rice-related data converted into GIS format | GIS file of rice and rice-related data from tabular format (excel, dbf, csv) converted into GIS format; Map layout of rice and rice-related data for visualization of spatial distribution patterns and temporal trends ; Integration of maps (whenever possible) to facilitate comprehensive analysis of the rice production situation in the Philippines; Work in close coordination with the Analytics section of DAC for a comprehensive spatio-temporal analysis, immediate supervisor and the DAC center chief. | Complete, accurate, and properly stored in DAC Data lake; | January to June 2026 | Within the Philippines | TCC-300-001
71 | J.E. Malangis | MFO 4. R&D Services | GIS Technical Staff | 2. Lead the spatio-temporal analysis of rice and rice-related data | Extracted statistics from the GIS and RS data submitted to the DAC Analytics section for input to DAC dashboard | GIS data used for dashboard developments and advanced spatio-temporal modelling and analysis | January to June 2026 | Within the Philippines | TCC-300-001
72 | J.E. Malangis | MFO 4. R&D Services | GIS Technical Staff | 3. Lead the organization and management of edited and analyzed GIS and RS data before submission for archiving to the central data storage of DAC | GIS database management and creation of metadata of all GIS and RS products; Developed and implemented data management strategies for storage and archive, inventory of existing GIS/RS data and organization of data types throughout the duration of the project; Complied with data protection regulations and best practices, maintaining the confidentiality and privacy of sensitive data. Submitted to Central DAC Data Storage all processed and analyzed data | Complete, accurate, and properly stored in DAC Data lake; | January to June 2026 | Within the Philippines | TCC-300-001
73 | J.E. Malangis | MFO 7. Improved Governance | Others (Training/Meetings/Compliance) | 4. Render service in the designated workstation and serve all working days within the contract duration from January to June 2025 | Rendered services in the designated workstation and serve all working days within contract duration from January to June 2025. | With documentation of attendance, and accomplishments reflected in the accomplishment report | January to June 2026 | Within the Philippines | TCC-300-001
74 | J.E. Malangis | MFO 7. Improved Governance | Others (Training/Meetings/Compliance) | 5. Provide an active line of communication with the supervisors | Maintained an active line of communication with the supervisors. | With no complaints from the supervisors | January to June 2026 | Within the Philippines | TCC-300-001
75 | J.E. Malangis | MFO 7. Improved Governance | Others (Training/Meetings/Compliance) | 6. Attend seminars, trainings, workshop and meetings as requested | Attended seminars, trainings, workshops and meetings. | With documented proof of attendance and participation or completion | As requested, within January to June 2026 | Within the Philippines | TCC-300-001
76 | J.E. Malangis | MFO 7. Improved Governance | Others (Training/Meetings/Compliance) | 7. Attend flag ceremony and all required institutional activities | Attended flag ceremony every Monday and other institutional activities | With documented proof of attendance and participation or completion | January to June 2026 | Within the Philippines | TCC-300-001
77 | J.E. Malangis | MFO 7. Improved Governance | Others (Training/Meetings/Compliance) | 8. Maintain safety, orderliness and cleanliness on work are at all times | Safety, orderliness, cleanliness on work area at all times are maintained. | based on institute guidelines and policies | January to June 2026 | Within the Philippines | TCC-300-001
78 | J.E. Malangis | MFO 7. Improved Governance | Others (Training/Meetings/Compliance) | 9. Cooperate and comply with PhilRice health and safety protocol | Cooperated and complied with PhilRice health and safety protocol. | based on institute guidelines and policies | January to June 2026 | Within the Philippines | TCC-300-001
79 | J.E. Malangis | MFO 7. Improved Governance | Others (Training/Meetings/Compliance) | 10. Perform other duties and responsibilities assigned from time to time | Performed other tasks that the immediate supervisor assigned from time to time. | With documentation of attendance, and accomplishments reflected in the accomplishment report | January to June 2026 | Within the Philippines | TCC-300-001
80 | J.E. Malangis | MFO 7. Improved Governance | Others (Training/Meetings/Compliance) | 11. Comply with IMS Policy, Procedures, Program and Projects of PhilRice | Complied with IMS Policy, Procedures, Program and Projects of Philrice. | based on ISO guideline | January to June 2026 | Within the Philippines | TCC-300-001
81 | J.E. Malangis | MFO 7. Improved Governance | Others (Training/Meetings/Compliance) | 12. Serve as a resource person during training, workshops, and seminars related to the project | Served as a resource person during training/workshops/seminars related to the project. | With documented proof of attendance and participation as instructor and training materials compiled | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
82 | J.E. Malangis | MFO 7. Improved Governance | Others (Training/Meetings/Compliance) | 13. Participate in meetings, training, and other activities organized by the projects or division; serve as resource person during workshops and training related to the projects | Participated in meetings, training and other activities organized by the projects or divisions and served as resource person during workshops and training related to the project | With documented proof of attendance and participation as instructor and training materials compiled | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
83 | J.E. Malangis | MFO 7. Improved Governance | Others (Training/Meetings/Compliance) | 14. Attend training provided internally or externally on skills enhancement | Attended training provided internally or externally on skills enhancement | With documented proof of attendance and participation or completion | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
84 | J.E. Malangis | MFO 7. Improved Governance | Others (Training/Meetings/Compliance) | 15. Provide technical support and implement other activities as deemed necessary | Provided technical support and assisted in the implementation of other activities as needed. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
85 | J.E. Malangis | MFO 7. Improved Governance | Others (Training/Meetings/Compliance) | 16. Participate in national or international scientific conferences | Participate in national or international scientific conferences. | With documented proof of attendance and participation or completion | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
86 | J.E. Malangis | MFO 7. Improved Governance | Others (Reporting) | 17. Provide monthly, semestral, and annual accomplishment/technical reports for the evaluation of the immediate supervisor | Submitted monthly/semestral/annual accomplishment/technical report to the immediate supervisor. | complete and accurate based on task given by supervisor | January to June 2026 | Within the Philippines | TCC-300-001
87 | K. Dela Cruz | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 1. Assist in exploration of new methodologies and model frameworks best suited for rice trajectory models | One (1) model framework for rice trajectory models produced. | complete with proper documentation | January to June 2026 | Within the Philippines | TCC-300-001
88 | K. Dela Cruz | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 2. Assist in data cleaning and preprocessing of local data needed for the rice trajectory model | One (1) dataset needed for modeling rice trajectories | Cleaned and pre-processed | January to June 2026 | Within the Philippines | TCC-300-001
89 | K. Dela Cruz | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 3. Assist in rice trajectory model deployment and monitoring and web app development | One (1) web application showing projections produced. One (1) set of projections generated from trajectory models | Projections and web application are complete and accessible through the RiceLytics Executive website | January to June 2026 | Within the Philippines | TCC-300-001
90 | K. Dela Cruz | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Sandbox | 4. Lead in at least one (1) regular ideation session | One (1) brief writeup of the featured topic/idea of the ideation session produced. | Brief writeup of the featured topic/idea. | January to June 2026 | Within the Philippines | TCC-300-001
91 | K. Dela Cruz | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Support Services (Consultation) | 5. Serve as consultant catering to consultation requests | Consultation services provided to 100% of clients assigned to staff. | Concern of client properly addressed and documented through the consultant's report and client feedback survey. | January to June 2026 | Within the Philippines | TCC-300-001
92 | K. Dela Cruz | MFO 3. Extension support, educations and traiing services (ESSETS) | DAC Training services | 6. Assist in the conduct of training services to PhilRice staff | At least one (1) training conducted. | With documented proof of attendance and participation as instructor and training materials compiled | By June 2026 | Within the Philippines | TCC-300-001
93 | K. Dela Cruz | MFO 3. Extension support, educations and traiing services (ESSETS) | Upscaling and development of Data Analytics Capabilities | 7. Assist and participate in coordination of activities and trainings under this collaborative project | One (1) activity/training/task accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
94 | K. Dela Cruz | MFO 4. R&D Services | Core Analytics (PhilRice Projects and other rice related data) | 8. Co Lead in development, maintenance of command center dashboards and shiny web apps related to PhilRice R&D Projects and other rice related data | One (1) dashboard/shiny web application developed and maintained. | Fully functional. Maintained and improved as necessary. | By June 2026 | Within the Philippines | TCC-300-001
95 | K. Dela Cruz | MFO 4. R&D Services | Core Analytics (PhilRice Projects and other rice related data) | 9. Lead the presentation and demonstration of command center dashboards and Shiny web applications focused on PhilRice R&D Projects and other rice related data intended clients | One presentation/demonstrations of shiny web app/dashboard conducted for intended cleints. | With proper documentation of presentation, and dashboard accessible through the RiceLytics Executive portal. | By June 2026 | Within the Philippines | TCC-300-001
96 | K. Dela Cruz | MFO 4. R&D Services | Rapid response Analytics (Operational Analytics) | 10. Lead data analysis of requests classified for rapid-response analytics focused on focused on rice farmers and their characteristics | Provided data analytics services to 100% of the rapid response analytics requests. | Provided data analytics services. | By June 2026 | Within the Philippines | TCC-300-001
97 | K. Dela Cruz | MFO 7. Improved Governance | Data Analytics on relevant rice industry news and current affairs (C) | 11. Lead in monitoring for data analytics potential and opportunities on news, policies and current affairs relating to rice industry | Provided relevant updates on rice data related news, policies and current affairs. | Updated weekly with proper documentation and accessible to other analytics unit members | January to June 2026 | Within the Philippines | TCC-300-001
98 | K. Dela Cruz | MFO 7. Improved Governance | Institution and Center Related Activities | 12. Assist in other project activities as instructed by the supervisor | Tasks assigned by the supervisor are accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
99 | K. Dela Cruz | MFO 7. Improved Governance | Institution and Center Related Activities | 13. Attend workshops or trainings as per invitation | Attended workshop or training as per invitation. | With documented proof of attendance, participation or completeion. | As per invitation, within January to June 2026 | Within the Philippines | TCC-300-001
100 | K. Dela Cruz | MFO 7. Improved Governance | Institution and Center Related Activities | 14. Participate in institutional activities | Participated in institutional activities. | As documented in attendance sheets | January to June 2026 | Within the Philippines | TCC-300-001
101 | K. Dela Cruz | MFO 7. Improved Governance | Institution and Center Related Activities | 15. Comply with Integrated Management System (IMS) Policy, Procedures, Programs, and Projects of PhilRice | Integrated Management System (IMS) Policy, Procedures, Programs and Projects of PhilRice are complied. | based on ISO guideline | January to June 2026 | Within the Philippines | TCC-300-001
102 | N.M. Francisco | MFO 2. Technologies | Advanced Analytics (Ensemble modelling) | 1. Co-lead in identification of data sources and data preprocessing for ensemble base models | Cleaned at least one (1) dataset needed for ensemble modelling. | With summary statistics computed and proper assessment conducted | January to June 2026 | Within the Philippines | TCC-300-001
103 | N.M. Francisco | MFO 2. Technologies | Advanced Analytics (Ensemble modelling) | 2. Co-lead in base model selection, training and evaluation | Generated model diagnostics and performance metrics of at least one (1) base model. | With documentation and interpration of generated model diagnostics and perofrmance metrics | January to June 2026 | Within the Philippines | TCC-300-001
104 | N.M. Francisco | MFO 2. Technologies | Advanced Analytics (Ensemble modelling) | 3. Co-lead in ensemble model construction, training and evaluation | One (1) preliminary ensemble model produced. Generated initial model diagnostics and performance metrics of one (1) ensemble model. | Preliminary ensemble model. Initial model diagnostics and performance metrics generated. | By June 2026 | Within the Philippines | TCC-300-001
105 | N.M. Francisco | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 4. Co-lead in exploration of new methodologies and model frameworks best suited for rice trajectory models | One (1) preliminary base model produced. | Preliminary base model tested with model diagnostics and documentation | By June 2026 | Within the Philippines | TCC-300-001
106 | N.M. Francisco | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 5. Co-lead in data cleaning and preprocessing of local data needed for the rice trajectory model | Cleaned at least one (1) variable/feature to be included in the model. | At least one (1) variable/feature to be included in the model is cleaned. | By June 2026 | Within the Philippines | TCC-300-001
107 | N.M. Francisco | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 6. Co-lead in rice trajectory model deployment and monitoring and web app development | Projections generated for one (1) month and/or one (1) scenario. One (1) report/table/analytics output/web app showing projections produced. | Projections using Rice Trajectory Model. Report/table/analytics output/web app produced. | January to June 2026 | Within the Philippines | TCC-300-001
108 | N.M. Francisco | MFO 2. Technologies | Advanced Analytics (Geoinformatics and spatial analytics) | 7. Assist in data exploration for spatio-temporal modelling of rice industry | One (1) dataset/feature/variable preprocessed needed for the spatio-temporal models | Dataset/feature/variable preprocessed for hyperlocal rice profiling. | January to June 2026 | Within the Philippines | TCC-300-001
109 | N.M. Francisco | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Sandbox | 8. Lead in at least one (1) regular ideation session | One (1) brief writeup of the featured topic/idea of the ideation session produced. | Brief writeup of the featured topic/idea. | January to June 2026 | Within the Philippines | TCC-300-001
110 | N.M. Francisco | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Sandbox | 9. Assist in documentation of one (1) regular ideation session | Written documentation of one (1) session outputs/discussions produced. | Written documentation of one (1) session outputs/discussions. | January to June 2026 | Within the Philippines | TCC-300-001
111 | N.M. Francisco | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Support Services (Consultation) | 10. Manage consultation requests, consultation schedule, consultant assignments and monitor feedback from clients | Monthly summary report of accomplishments produced. Consultation services provided to 100% of clients assigned to staff. | Concern of client properly addressed and documented through the consultant's report and client feedback survey. | January to June 2026 | Within the Philippines | TCC-300-001
112 | N.M. Francisco | MFO 3. Extension support, educations and traiing services (ESSETS) | DAC Training services | 11. Served as trainer/instructor for training services offered by DAC | One (1) Training attended as instructor. | With documented proof of attendance and participation as instructor and training materials compiled | By June 2026 | Within the Philippines | TCC-300-001
113 | N.M. Francisco | MFO 4. R&D Services | Core Analytics (Operational Analytics) | 12. Lead in data analysis of tables, graphs, data visualizations, maps and other analytics outputs needed by the data products team | Provided data analytics services to 100% of the needed analytics request. | Provision of data analytics support to Data Products properly documented in the accomplishment report | January to June 2026 | Within the Philippines | TCC-300-001
114 | N.M. Francisco | MFO 4. R&D Services | Core Analytics (Operational Analytics) | 13. Lead in reviewing core analytics output and data quality assurance | Reviewed 100% of the analytics output released under core analytics. | All outputs, revisions and feedback are properly documented | January to June 2026 | Within the Philippines | TCC-300-001
115 | N.M. Francisco | MFO 4. R&D Services | Core Analytics (Operational Analytics) | 14. Supervise development and maintenance of analytics dashboards and shiny web apps for command center | One (1) analytics shiny web app or dashboard developed or maintained. | Fully functional. Maintained and improved as necessary. | By June 2026 | Within the Philippines | TCC-300-001
116 | N.M. Francisco | MFO 4. R&D Services | Core Analytics (Operational Analytics) | 15. Oversee demonstration and presentation of analytics dashboards and shiny web apps to intended clients | One (1) analytics shiny web app or dashboard presented or demonstrated. | Presented or demonstrated to clients, accessible through the RiceLytics Executive portal. | By June 2026 | Within the Philippines | TCC-300-001
117 | N.M. Francisco | MFO 4. R&D Services | Core Analytics (Operational Analytics) | 16. Lead in reporting monthly accomplishments of Core Analytics | Monthly summary report of accomplishments produced | Monthly reports submitted to DAC PMO, and presented during monthly meetings | January to June 2026 | Within the Philippines | TCC-300-001
118 | N.M. Francisco | MFO 4. R&D Services | Rapid response Analytics (Operational Analytics) | 17. Lead in reporting monthly accomplishments of Rapid-response Analytics | Monthly summary report of accomplishments produced | Monthly reports submitted to DAC PMO, and presented during monthly meetings | January to June 2026 | Within the Philippines | TCC-300-001
119 | N.M. Francisco | MFO 4. R&D Services | Rapid response Analytics (Operational Analytics) | 18. Lead in data analysis of requests classified for rapid-response analytics | Provided data analytics services to 100% of the rapid response analytics requests. | With documentation report for each rapid resonse | January to June 2026 | Within the Philippines | TCC-300-001
120 | N.M. Francisco | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 19. Lead the operations, services and projects and task management of Data Analytics Center – Analytics Unit | All Analytics unit outputs and targets accomplished. | based on DAC standards and guidelines. | within set timelines | Within the Philippines | TCC-300-001
121 | N.M. Francisco | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 20. Represent the Analytics unit in meetings where attendance of DAC-Analytics unit is needed | Meetings attended as representative of DAC Analytics unit. | with complete documentations and resolutions, when needed | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
122 | N.M. Francisco | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 21. Report the status of activities and accomplishments of Analytics unit when needed | One (1 set) of presentations or reports on summary of accomplishments submitted. | Complete and accurate. | January to June 2026 | Within the Philippines | TCC-300-001
123 | N.M. Francisco | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 22. Lead in the unit review of Analytics unit outputs | Written documentations and resolution on internal review of analytics unit outputs produced. | Written documentations and resolution on internal review of analytics unit outputs. | January to June 2026 | Within the Philippines | TCC-300-001
124 | N.M. Francisco | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 23. Ensure all analytics unit processes are documented, data used are retrieved solely from the DAC data warehouse and newly generated data and data products are properly stored in the DAC data warehouse | 100% of Analytics output stored in DAC data warehouse. Written SOPs, guidelines, and manuals for Analytics unit processes produced. | All analytics outputs, SOPs, guidelines and manuals created are accessible and properly documented in the centralized data warehouse. | January to June 2026 | Within the Philippines | TCC-300-001
125 | N.M. Francisco | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 24. Ensure that data-related policies are strictly followed in all analytics unit processes and outputs | 100% of Analytics unit processes and outputs approved by the Data governance staff. | Outputs are compliant with data-related policies, with proper documentation. | January to June 2026 | Within the Philippines | TCC-300-001
126 | N.M. Francisco | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 25. Ensure accurate communication of all data products and analytics report, minimizing misinterpretation when these products are utilized across different media and platforms | 100% of Writeups, reports, Analytics unit outputs and data products approved. | Complete, accurate and with proper documentation | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
127 | N.M. Francisco | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 26. Assist center management and other units in other institutional and center related activities not led by the Analytics unit | Activities of DAC management and other units assisted. | Provided support in a timely and satisfactory manner, reflected in the accomplishment report | January to June 2026 | Within the Philippines | TCC-300-001
128 | N.M. Francisco | MFO 7. Improved Governance | Upscaling and development of Data Analytics Capabilities | 27. Assist and participate in coordination of activities and trainings under this collaborative project | One (1) activity/training/task accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
129 | N.M. Francisco | MFO 7. Improved Governance | Institution and Center Related Activities | 28. Assist in other project activities as instructed by the supervisor | Tasks assigned by the supervisor are accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
130 | N.M. Francisco | MFO 7. Improved Governance | Institution and Center Related Activities | 29. Attend workshops or trainings as per invitation | Attended workshop or training as per invitation. | With documented proof of attendance, participation or completeion. | As per invitation, within January to June 2026 | Within the Philippines | TCC-300-001
131 | N.M. Francisco | MFO 7. Improved Governance | Institution and Center Related Activities | 30. Participate in institutional activities | Participated in institutional activities. | As documented in attendance sheets | January to June 2026 | Within the Philippines | TCC-300-001
132 | N.M. Francisco | MFO 7. Improved Governance | Institution and Center Related Activities | 31. Comply with Integrated Management System (IMS) Policy, Procedures, Programs, and Projects of PhilRice | Integrated Management System (IMS) Policy, Procedures, Programs and Projects of PhilRice are complied. | based on ISO guideline | January to June 2026 | Within the Philippines | TCC-300-001
133 | R. Asirot | MFO 2. Technologies | Advanced Analytics (Ensemble modelling) | 1. Assist in ensemble model construction, training and evaluation | One (1) ensemble model for production, area and yield (PAY) | With generated ensemble model diagnostics, performance metrics and model predictions. | January to June 2026 | Within the Philippines | TCC-300-001
134 | R. Asirot | MFO 2. Technologies | Advanced Analytics (Ensemble modelling) | 2. Assist data preprocessing for ensemble base models | One (1) dataset to be used for ensemble modelling. | Cleaned and pre-process dataset. | January to June 2026 | Within the Philippines | TCC-300-001
135 | R. Asirot | MFO 2. Technologies | Advanced Analytics (Ensemble modelling) | 3. Assist in base model selection, training and evaluation | One (1) base model used for ensemble modelling | With generated model diagnostics, performance metrics and model predictions. | By June 2026 | Within the Philippines | TCC-300-001
136 | R.H. Caliwagan | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 1. Lead in reporting monthly accomplishments under this function/project | Monthly summary report of accomplishments produced | Monthly reports submitted to unit head, and presented during monthly meetings | January to June 2026 | Within the Philippines | TCC-300-001
137 | R.H. Caliwagan | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 2. Lead in exploration of new methodologies and model frameworks best suited for rice trajectory models | One (1) model framework for rice trajectory models produced. | complete with proper documentation | January to June 2026 | Within the Philippines | TCC-300-001
138 | R.H. Caliwagan | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 3. Lead in data cleaning and preprocessing of local data needed for the re-estimation of Rice trajectory Models | One (1) dataset needed for modeling rice trajectories | Cleaned and pre-processed | January to June 2026 | Within the Philippines | TCC-300-001
139 | R.H. Caliwagan | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 4. Lead in rice trajectory model deployment and monitoring and web app development | One (1) web application showing projections produced. One (1) set of projections generated from trajectory models | Projections and web application are complete and accessible through the RiceLytics Executive website | January to June 2026 | Within the Philippines | TCC-300-001
140 | R.H. Caliwagan | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 5. Lead in multiple component model selections, training and evaluation | One (1) component model produced. | With generated model diagnostics, performance metrics and model predictions. | January to June 2026 | Within the Philippines | TCC-300-001
141 | R.H. Caliwagan | MFO 2. Technologies | Advanced Analytics (Modelling trajectories) | 6. Lead in combining system of models, training and evaluation of combined projections from trajectory models | One (1) combined rice trajectory model | With generated model diagnostics, performance metrics and model predictions. | January to June 2026 | Within the Philippines | TCC-300-001
142 | R.H. Caliwagan | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Sandbox | 7. Lead in one (1) regular ideation session | One (1) brief writeup of the featured topic/idea produced. | Brief writeup of the featured topic/idea. | January to June 2026 | Within the Philippines | TCC-300-001
143 | R.H. Caliwagan | MFO 3. Extension support, educations and traiing services (ESSETS) | Analytics Support Services (Consultation) | 8. Manage consultation requests, consultation schedule, consultant assignments and monitor feedback from clients | Consultation services provided to 100% of clients assigned to staff. | Concern of client properly addressed and documented through the consultant's report and client feedback survey. | January to June 2026 | Within the Philippines | TCC-300-001
144 | R.H. Caliwagan | MFO 3. Extension support, educations and traiing services (ESSETS) | DAC Training services | 9. Assist in the conduct of training services to PhilRice staff | At least one (1) training conducted. | With documented proof of attendance and participation as instructor and training materials compiled | By June 2026 | Within the Philippines | TCC-300-001
145 | R.H. Caliwagan | MFO 4. R&D Services | Core Analytics (Market and Economics) | 10. Lead in development, maintenance of command center dashboards and shiny web apps related to Market and Economics | One (1) dashboard/shiny web application developed and maintained. | Fully functional. Maintained and improved as necessary. | By June 2026 | Within the Philippines | TCC-300-001
146 | R.H. Caliwagan | MFO 4. R&D Services | Core Analytics (Market and Economics) | 11. Lead the presentation and demonstration of command center dashboards and Shiny web applications focused on Market and Economic insights to the intended clients | One presentation/demonstrations of shiny web app/dashboard conducted for intended cleints. | With proper documentation of presentation, and dashboard accessible through the RiceLytics Executive portal. | January to June 2026 | Within the Philippines | TCC-300-001
147 | R.H. Caliwagan | MFO 4. R&D Services | Rapid response Analytics (Operational Analytics) | 12. Lead data analysis of requests classified for rapid-response analytics related to Market and Economics | Provided data analytics services to 100% of the rapid response analytics requests related to Market and Economics | With documentation report for each rapid resonse | January to June 2026 | Within the Philippines | TCC-300-001
148 | R.H. Caliwagan | MFO 4. R&D Services | External Project (Planning, Monitoring, and Evaluation of MR) | 13. Co-work in the write-up of the MR national monograph | Write up for the national monograph produced. | National monograph finalized, complete and with proper documentation | January to June 2026 | Within the Philippines | TCC-300-001
149 | R.H. Caliwagan | MFO 4. R&D Services | External Project (Planning, Monitoring, and Evaluation of MR) | 14. Co-work in the continuous improvement of deployment strategies and design in all target areas | Deployment strategies for MR produced. | Continuous improvement of deployment strategies and design. | January to June 2026 | Within the Philippines | TCC-300-001
150 | R.H. Caliwagan | MFO 4. R&D Services | External Project (The Evolving Philippine Rice Economy) | 15. Assist in the data processing and generation of results | Data processed and output tables produced. | Output tables are complete, accurate, and approved by project team | January to June 2026 | Within the Philippines | TCC-300-001
151 | R.H. Caliwagan | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 16. Represent the Analytics unit in meetings where attendance of DAC-Analytics unit is needed, in the absence of the unit head | Meeting/s attended in the absence of the unit head. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
152 | R.H. Caliwagan | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 17. Report the status of activities and accomplishments of Analytics unit when needed, in the absence of the unit head | 1 unit summary report of accomplishments, when needed. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
153 | R.H. Caliwagan | MFO 7. Improved Governance | Analytics Unit Leadership and Management | 18. Co-lead review of all Analytics unit outputs, reports, dashboards, analysis and data products | Written documentations and resolution on internal review of analytics unit outputs produced. | Written documentations and resolution on internal review of analytics unit outputs. | January to June 2026 | Within the Philippines | TCC-300-001
154 | R.H. Caliwagan | MFO 7. Improved Governance | Data Liaison | 19. Co-Lead in data liaising, coordinating with Data Lake unit, and monitoring of all available data to be used for all analytics projects and tasks within the unit | Facilitated the monitoring and management of all required data for the Analytics Unit. | Facilitated monitoring and management in collaboration with the Data Lake Unit. | January to June 2026 | Within the Philippines | TCC-300-001
155 | R.H. Caliwagan | MFO 7. Improved Governance | Upscaling and development of Data Analytics Capabilities | 20. Assist and participate in coordination of activities and trainings under this collaborative project | One (1) activity/training/task accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
156 | R.H. Caliwagan | MFO 7. Improved Governance | Institution and Center Related Activities | 21. Assist in other project activities as instructed by the supervisor | Tasks assigned by the supervisor are accomplished. | With documentation reflected on accomplishment reports | As needed, within January to June 2026 | Within the Philippines | TCC-300-001
157 | R.H. Caliwagan | MFO 7. Improved Governance | Institution and Center Related Activities | 22. Attend workshops or trainings as per invitation | Attended workshop or training as per invitation. | With documented proof of attendance, participation or completeion. | As per invitation, within January to June 2026 | Within the Philippines | TCC-300-001
158 | R.H. Caliwagan | MFO 7. Improved Governance | Institution and Center Related Activities | 23. Participate in institutional activities | Participated in institutional activities. | As documented in attendance sheets | January to June 2026 | Within the Philippines | TCC-300-001
159 | R.H. Caliwagan | MFO 7. Improved Governance | Institution and Center Related Activities | 24. Comply with Integrated Management System (IMS) Policy, Procedures, Programs, and Projects of PhilRice | Integrated Management System (IMS) Policy, Procedures, Programs and Projects of PhilRice are complied. | based on ISO guideline | January to June 2026 | Within the Philippines | TCC-300-001